## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | team-project-2185-swen-261-08-b-thecompilers

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Testers In Class | Sprint3 | Tester initials; date; comments (required if test failed)
As a player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | EMC; 3/3/2019 | Pass | EMC; 3/3/2019 | Pass | Pass | KAK 4/17/19
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Signin page, with a means to enter a player name. | Pass | EMC; 3/3/2019 | Pass | EMC; 3/3/2019 | Pass | Pass | KAK 4/17/19
| Given that no one else is using my name when I enter my name in the sign-in form and click the Sign-in button then I expect system to reserve my name and navigate back to the Home page. | Pass | EMC; 3/3/2019 | Pass | EMC; 3/3/2019 | Pass | Pass | KAK 4/17/19
| Given that no one else is using my name when I enter a name with a double quote (`"`) then I expect the system to reject this name and return the sign-in form. (Note: double quote is not a valid character in a Player's name.) | Pass | EMC; 3/3/2019 | Pass | EMC; 3/3/2019 | Pass | Pass | KAK 4/17/19
| Given that someone else with my name has signed-in when I enter my name in the sign-in form then I expect the system to reject my sign-in and return the sign-in form. I can then choose a different user name. | Pass | EMC; 3/3/2019 | Pass | EMC; 3/3/2019 | Pass | Pass | KAK 4/17/19
| Given that I have signed in when I see the Home page then I must see a means to sign-out. (such as a link or button) Thus the sign-in and sign-out links need to alternate and never been seen together or not at all. | Pass | HM; 3/3/2019 | Pass | HM; 3/3/2019 | Pass | Pass | KAK 4/17/19
| Given that I am signed-in when I click on the sign-out link then I expect the system to sign me out, release my name for use by other users, and then return me to the Home page. | Pass | HM; 3/3/2019 | Pass | HM; 3/3/2019 | Pass | Pass | KAK 4/17/19
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | KAK; 3/3/2019 | Pass | KAK; 3/3/2019 | Pass | Pass | KAK 4/17/19
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | KSQ; 3/3/2019 | Pass | KSQ; 3/3/2019 | Pass | Pass | KAK 4/17/19
As a player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | YL; 3/4/2019 | Pass | YL; 3/4/2019 | Pass | Pass | KAK 4/17/19
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | KAK; 3/4/2019 | Pass | KAK; 3/4/2019 | Pass | Pass | KAK 4/17/19
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | KAK; 3/4/2019 | Pass | HM; 3/30/2019 | Pass | Pass | KAK 4/17/19
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View from the Home page. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | YL; 3/4/2019 | Pass | YL; 3/4/2019 | Pass | Pass | KAK 4/17/19
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | YL; 3/4/2019 | Pass | YL; 3/4/2019 | Pass | Pass | KAK 4/17/19
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | KAK; 3/4/2019 | Pass | KAK; 3/4/2019 | Pass | Pass | KAK 4/17/19
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | YL; 3/4/2019 | Pass | YL; 3/4/2019 | Pass | Pass | KAK 4/17/19
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | KAK; 3/4/2019 | Pass | KAK; 3/4/2019 | Pass | Pass | KAK 4/17/19
As a player I want to be able to make a simple move. | Given it is my turn when I am playing the game then I want to be able to make a simple move. |  |  | Pass | HM; 3/30/2019 | Pass | Pass | KAK 4/17/19
| Given that my piece is a Single piece when I make a move then I should only move diagonally forward. |  |  | Pass | HM; 3/30/2019 | Pass | Pass | KAK 4/17/19
| Given that my piece is a King piece when I make a move then I should be able to move both diagonally forward and backward. |  |  | Pass | HM; 3/30/2019 | Pass | Pass | KAK 4/17/19
As a player I want to be able to make a single jump move. | Given it is my turn when I am playing the game then I want to be able to make a single jump move. |  |  | Pass | HM; 3/30/2019 | Pass | Pass | KAK 4/17/19
| Given I jumped over another player's piece when I made a valid jump move over them then I want to capture that piece. |  |  | Pass | HM; 3/30/2019 | Pass | Pass | KAK 4/17/19
As a player I want to be able to make a multiple jump move. | Given it is my turn when I am playing the game then I want to be able to make a multiple jump move. |  |  | Pass | HM; 3/30/2019 | Pass | Pass | KAK 4/17/19
| Given I jumped over another player's piece when I made a valid jump move over them then I want to capture that piece. |  |  | Pass | HM; 3/30/2019 | Pass | Pass | KAK 4/17/19
As a player I want to quit the game so that I can start to do other work. | Given that I got other work to do when I am playing the game then I want to quit the game and do my work. |  |  | Pass | HM; 3/30/2019 | Pass | Pass | KAK 4/17/19
As a player I must be able to win the game so that there is a definite winner. | Given that the opponent cannot make a move either because all the opponent's pieces have been captured or if all the pieces of the opponent are blocked in when I am still playing then I want to be able to win the game. |  |  | Pass | HM; 3/30/2019 | Pass | Pass | KAK 4/17/19
|  |  |  | Pass | HM; 3/30/2019 | Pass | Pass | KAK 4/17/19
As a player I want to see a notification that it is my turn so that I know when I can move a piece. | Given it is my turn when I am playing the game then I want to be notified that it's my turn. |  |  | Pass | HM; 3/30/2019 | Pass | Pass | KAK 4/17/19
As a player I want to be able to select a game piece so that I can move that piece. | Given it is my turn when I am playing the game then I want to select the piece I want to move. |  |  | Pass | HM; 3/30/2019 | Pass | Pass | KAK 4/17/19
As a player I want to learn the rules so that I can play the game. | Given I am playing the game when I don't know the rules then I want to be able to check the rules. |  |  | Pass | HM; 3/30/2019 | Pass | Pass | KAK 4/17/19
As a player I want to move forward or backward two steps diagonally if there is an opponent piece right next to me diagonally so that I attack that opponent piece. | Given that there is a opponent piece right next to me diagonally (backward or forward) when it is my turn then I must be able to attack that opponent piece. |  |  | Pass | HM; 3/30/2019 | Pass | Pass | KAK 4/17/19
As a player I want to be notified if I try to make an invalid move so that I can make a different move. | Given that there is already a piece on the space where I try to drag my piece then I cannot place my piece. |  |  | Pass | HM; 3/30/2019 | Pass | Pass | KAK 4/17/19
| Given that I try to place a piece on a white space then I must not be able to do so. |  |  | Pass | HM; 3/30/2019 | Pass | Pass | KAK 4/17/19
| Given that I try to move my piece horizontally or vertically then I must not be able to do so. |  |  | Pass | HM; 3/30/2019 | Pass | Pass | KAK 4/17/19
As a player I want my piece to be a single piece until it reaches the furthest row on the opponent's side so that it can only move forward and not backward. | Given that a piece has not reached the furthest row on the opponent's side when I am playing then I want the single piece to only make a forward diagonal single move. |  |  | Pass | HM; 3/30/2019 | Pass | Pass | KAK 4/17/19
As a player I want to be able to submit my move. | Given that I have decided my move then I must be able to finalize and submit my move. |  |  | Pass | HM; 3/30/2019 | Pass | Pass | KAK 4/17/19
As a player I want to move first if I have red pieces so that the game starts and I do not lose the game. | Given that I have red pieces when the game start then I want to be able to move first. |  |  | Pass | HM; 3/30/2019 | Pass | Pass | KAK 4/17/19
| Given that I am the white player when the game starts then I should not be able to move first. |  |  | Pass | HM; 3/30/2019 | Pass | Pass | KAK 4/17/19
(In Progress) As a player, I want to be able to play against an AI player so that I can play alone if I wish | Given that I am logged in, I want to be able to see an option to play against an AI | [5 empty] | Pass | KAK 4/17/19
AI | Given that I have selected the AI option, start a game against an AI player | [5 empty] | Pass | KAK 4/17/19
| Given that I am playing against the AI, I must be able to move my pieces as though it were a normal game | [5 empty] | Pass | KAK 4/17/19
| Given that it is an AI's turn it takes a jump move if there is one possible. | [5 empty] | Pass | KAK 4/17/19
| Given that it is an AI's turn it makes a multiple jump move if possible | [5 empty] | Pass | KAK 4/17/19
| Given that it is an AI's turn it makes a simple move if no jump move is possible. | [5 empty] | Pass | KAK 4/17/19
| Given that I am playing against the AI, when I click submit turn, the AI must make a valid move before it becomes my turn again | [5 empty] | Pass | KAK 4/17/19
(In Progress) As a player, I want to be able to watch another game as a spectator so that I dont have to play a game to participate | Given that I am logged in, and another game is in progress, I want to be able to see an option to view the game as a spectator | [5 empty] | Pass | KAK 4/17/19
SPECTATOR | Given that I have selected the spectator option, I want to be able to view the current state of the game | [5 empty] | Pass | KAK 4/17/19
| Given that I am currently viewing a game, I must not be able to modify the game in any way | [5 empty] | Pass | KAK 4/17/19
(In Progress) As a player, I want to be able to recieve a hint about where to move so that I can play checkers better | Given that I am currently in a game, I want to see an option to recieve a hint | [5 empty] | Pass | KAK 4/17/19
HINT | Given that I have selected the help option, I must be able to see at least one valid move I can make. | [5 empty] | Pass | KAK 4/17/19